## Slide 1
LUFTHANSA TERADATA → DATABRICKS MIGRATION · REFERENCE DOCUMENTATION
The Teradata Defect & Out-of-Scope Item Tracker
How the all-pods tracker works, and what 18 logged items are actually telling us about where migration defects come from.
OWNER All Pods — Shared Tracker
DATE Snapshot as of latest export
TRACK Reference Documentation · Defect Tracking

## Slide 2
SESSION MAP
What this deck covers
What the tracker is for, and who it's for
Anatomy of a tracker row — every column explained
The three item types it captures, with real examples
A data snapshot: status, priority, and effort across all 18 logged items
The recurring pattern hiding in plain sight — and two defects that hit every stream
How to log a new item correctly, and when to escalate outside the tracker
02

## Slide 3
PURPOSE
What the tracker is for
①
One shared list, across every pod
A single source of truth for Teradata defects, change requests, and out-of-scope items — not a per-squad spreadsheet that only your pod can see.
②
Traceability from symptom to fix
Each row carries the defect description, its root cause, who owns it, and what action actually closed it — so the next person who hits something similar doesn't start from zero.
③
A record for planning, not just fixing
Effort (hours) and Timeline (days) columns turn this into real data for scoping future migration waves, not just a to-do list.
03

## Slide 4
STRUCTURE
Anatomy of a tracker row
Identity: Sl. No., Raised by, Community, Squad, Stream — pins the item to an exact place in the migration.
Classification: Type (Teradata Defect / CR / Architecture Discussion), Description, Priority.
Ownership: Ticket Id/Link, Owner, Status (Done / In-Progress).
Cost: Effort (in Hrs), Timeline (in Days) — actuals, not estimates.
Resolution: RCA, Action / Remarks — the part most useful to the next person.
04

## Slide 5
CLASSIFICATION
The three item types — with real examples
Teradata Defect
16 of 18 logged items — by far the most common type
e.g. non-deterministic surrogate keys, timestamp time-zone conversion
Something Teradata itself did that Databricks can't reproduce or shouldn't inherit
CR (Change Request)
e.g. IMP_SAMBA — adding columns and their logic changes
A genuine scope change, not a bug — usually needs back-and-forth with Lufthansa on timing
Architecture Discussion
e.g. how to send stream-native emails — 3 proposed approaches, still unresolved
Open design questions that need a decision, not a code fix
05

## Slide 6
SNAPSHOT
18 items logged — where they actually stand
15 / 18
Items marked Done
3 / 18
Still In-Progress
272 hrs
Total effort logged to date
Average effort per item is just over 15 hours — but that average hides a wide spread: several items closed in 4 hours, while one architecture discussion has already run to 100 hours and 60 days without a decision.
06

## Slide 7
PRIORITY BREAKDOWN
Where the urgency actually sits
2
Critical — both closed (folder-structure change, timestamp UTC conversion)
15
High — the overwhelming majority of logged items
1
Normal — the one item Lufthansa marked Out of Scope
07

## Slide 8
THE PATTERN HIDING IN PLAIN SIGHT
Non-deterministic surrogate keys — 8 of 18 items, 3 communities
Community 5: IMP_AVAILABILITY and its three variants (LX, OS, SN) — surrogate IDs in Teradata weren't unique.
Community 2: IMP_COSMA_PARTNERS and IMP_IATCI_STATISTICS — a key generated by ROW_NUMBER() in Teradata with no unique record identification, used downstream in sequencing.
Community 9: IMP_JV_APLUS_DAILY and IMP_JV_APLUS_WEEKLY — random surrogate keys generated in the Teradata stream, requiring both the Teradata and Databricks streams to be fixed.
Same root cause, raised independently three times by three different people, in three different communities — before anyone connected them.
THE LESSON
Check the tracker for this pattern before starting a fresh RCA on a key/sequencing issue.
Non-deterministic key generation is now a known class, not a surprise.
08

## Slide 9
GENERAL DEFECTS — AFFECTS 'ALL'
Two defects that hit every stream, not just one
Folder-structure change (Critical, Done)
Teradata introduced new subfolders in its data export
The data_load utility failed to iterate sub-folders — developers had to manually create recon tables and load data
16 hours, 3 days to resolve across all affected streams
Berlin → UTC timestamp conversion (Critical, Done)
Data exported by Teradata had all timestamp columns converted from Berlin/Europe to UTC, impacting data validation
Required additional casting during data load — which still resulted in minute deviations
24 hours, 4 days — this is the same defect class covered in the Conversion Rulebook (TIMESTAMP_NTZ)
09

## Slide 10
OUTLIER WORTH WATCHING
Stream-native emails: 100 hours, 60 days, still open
Logged as an Architecture Discussion, not a defect — the question is how to send stream-native emails at all.
Three different approaches have already been proposed and worked through, and shown to Lufthansa — none accepted, requiring multiple iterations and discussions.
At 100 hours and 60 days, this is by far the largest single item in the tracker — roughly 37% of all effort logged across all 18 items.
This is a design-decision bottleneck, not an engineering one — escalate for a decision rather than continuing to iterate on new approaches.
10

## Slide 11
CASE STUDY
INT_BOARDED_PAX — when the bug isn't yours to fix
The Teradata stream had been generating erroneous output for three years before Databricks even started converting it.
When the code errors were highlighted to Lufthansa as an in-scope stream issue, the response was that the same issue had been occurring for three years with no changes implemented in that time.
Resolution: Lufthansa marked the stream Out of Scope, and a change board ticket was raised — this is not something the migration team can or should fix silently.
Takeaway: a mismatch against Teradata isn't automatically a migration defect. Sometimes Databricks is correctly reproducing a Teradata bug that predates the project.
11

## Slide 12
PROCESS
How to log a new item — and when to escalate
1
Check for the pattern first
Before starting a fresh RCA, scan the tracker for a similar description, stream type, or root cause — the surrogate-key pattern was raised three times before anyone noticed it was one issue.
2
Fill every required column
Community, Squad, Stream, Type, Description, Priority, and Owner at minimum — Effort and Timeline once the item closes.
!
Escalate Critical items immediately
Don't just log and wait — a Critical item (like the folder-structure or timestamp defects) affects every stream and needs immediate visibility beyond the tracker.
12

## Slide 13
KEY TAKEAWAYS
Cheat-sheet for using the tracker well
✓
One shared tracker across all pods — check it before opening a new investigation.
✓
15 of 18 items are Done; 272 hours logged to date; average ~15 hrs/item, but the spread is wide.
✓
Teradata Defect is the dominant type (16 of 18) — CRs and architecture discussions are rarer but often bigger.
✓
Non-deterministic surrogate key generation has already hit 3 communities independently — treat it as a known class.
✓
Two Critical defects (folder structure, Berlin→UTC timestamps) affect every stream, not just one.
✓
The stream-native email discussion alone accounts for ~37% of all effort logged — it needs a decision, not more iteration.
✓
Not every mismatch is a migration bug — INT_BOARDED_PAX shows Lufthansa can and will mark a stream Out of Scope.
✓
Log Community/Squad/Stream/Type/Priority/Owner at minimum, and escalate Critical items immediately, not just in the tracker.
13