## Slide 1
LUFTHANSA GROUP DATA MIGRATION PROGRAM · NEW JOINER ENABLEMENT
SESSION 1
Program Overview
Communities, Streams, Squads & Families
Recorded Aug 31, 2026, 8:29 AM · ~1hr with the newly onboarded pod
What's inside this deck
SESSION 1
1
✓
Why this program exists
✓
Program structure
✓
Squad definitions
✓
Waves & freeze periods
✓
Life of one stream
✓
Open questions

## Slide 2
CONTEXT
Why this training program exists
The gap it addresses: a number of team members onboarded after day one hadn't been fully grounded or trained on project fundamentals — which was slowing scope completion, even though the frameworks and tooling were solid.
Two-week bootcamp
A focused, mandatory 2-week training plan for everyone newly onboarded (even yesterday) or not yet up to speed — regardless of role or seniority.
Independent contributor by week 3
Goal: by the end of week 2, every participant has a full project brief and hands-on practice, and can own a stream independently from week 3.
Measured & iterated daily
Attendance, participation, and unanswered questions are reviewed after each session so the remaining sessions can be tuned.
Recorded for reuse
Sessions run on the CT tenant so they can be recorded, documented, and turned into reference material — including this deck.
PROGRAM OVERVIEW
2

## Slide 3
THE PROGRAM
The project at a glance
Lufthansa Group runs one centralized analytical data warehouse (the “ADW” / Teradata estate) serving ~10–12 airline carriers (LX, OS, SN, 4Y, and others). The program is a complete lift-and-shift of that estate onto Azure Databricks — not a modernization.
100%
Logic parity required — every Teradata calculation must produce the same result on Databricks
350–400
End-to-end jobs (“streams”) to migrate, across ~30,000–40,000 tables
2,000+
Downstream reports consume this data today — nothing can silently change
11
Communities (milestones) the program is broken into, community 0 – 10
Tech stack: Azure Databricks · Unity Catalog · Delta Lake · Databricks Asset Bundles · serverless jobs · Databricks CLI · Codex (AI code-review agent)
Three environments you'll live in
Dev
Where you build: conversion, testing, validation, reconciliation, integration runs.
Pre-prod
A parallel-run environment: your stream and the live Teradata stream run side by side daily, with a generated comparison report.
UAT / Prod sign-off
After 3 consecutive days of 100% validated pre-prod data, Lufthansa reviews, tests, and signs off.
PROGRAM OVERVIEW
3

## Slide 4
THE PROGRAM
How the program is broken down
Three nested units of work — learn these terms first, everything else builds on them.
STREAM
The atomic unit
One end-to-end Databricks job: conversion, testing, validation, reconciliation, deployment, and UAT for one data pipeline. Each has an individually responsible owner.
COMMUNITY
A milestone
A group of streams released together (Community 0 – 10). Communities are sequenced by dependency, not by number — a community can't ship before what it depends on has.
SQUAD
A business domain
A horizontal grouping by subject area (ADW, B2B, Loyalty, Network, Reservations, RM, Sales, and more). Every stream in every community belongs to exactly one squad.
Each community can contain a different number of streams from each squad — e.g. 20 ADW streams + 10 B2B streams + 5 Loyalty streams in the same community.
PROGRAM OVERVIEW
4

## Slide 5
THE PROGRAM
Meet the squads
Squads map to airline business functions — think of them the way Sales, Finance, or Logistics map to a normal enterprise.
Squad | What it owns | Squad lead (as of this session)
ADW (core) | Core central flight & reference data — the backbone. Booking data (Amadeus-style aggregators): scheduled flights, bookings, seats. | Vijay
B2B | Corporate & business travel — company deals and dedicated booking portals. | Vijay
Loyalty | Loyalty programs, e.g. Miles & More. PPL is folded into this squad, not tracked separately. | Prashant
Network | Alliance partners and traffic between carriers. | Prashant
Reservations | PNRs and booking-related information. | Bulbul
RM (Revenue Mgmt) | Revenue management and pricing. | Bulbul
Sales | Ticket sales and revenue accounting. | Rajat
Squad 1 / Squad 3 | Small streams: flight ops, airport ops, data marts, day-to-day operations. “Ancillaries & Misc” covers shared tables. | Rajat
PROGRAM OVERVIEW
5

## Slide 6
THE PROGRAM
Communities ship in dependency order, not number order
Streams depend on each other, exactly like table lineage: a stream can't go to pre-prod before the streams it reads from are already there. A full lineage document exists so you can look up any stream's dependencies.
Wave-based deployment inside one community
Wave 1
Wave 2
Wave 3
Wave 4
Wave 5
Independent streams deploy first (Wave 1); anything dependent on them waits until its prerequisite wave is live in pre-prod.
Freeze periods
Once a community is “freezed” (e.g. Communities 2, 5, 9, 10 at the time of this session), the client cannot request changes to those streams without an explicit heads-up from the program. Always confirm with your pod lead before touching a freezed stream — otherwise reconciliation numbers stop matching.
Snapshot at time of recording: Community 10 — deployed, UAT signed off, running in pre-prod. Community 9 — ~8–10 streams, completed. Community 5 — ~20–25 streams, deployed to UAT, minor sign-offs pending. No active development on 5, 9, or 10 beyond bug fixes.
PROGRAM OVERVIEW
6

## Slide 7
THE PROGRAM
The life of one stream, end to end
1
Prerequisites
Confirm repo & data access. Get Teradata reference script + converted code. Get DDLs deployed to dev.
2
Convert
Use Brickify to convert Teradata SQL to Databricks. LLM-assisted, so always check against the source script.
3
Review & fix
Run Codex for a logic-parity and code-quality check; apply suggested fixes.
4
Unit test & validate
Run against recon tables via AVF until you hit 100% match (or an agreed exception).
5
PR & pre-prod
Pod lead + ops + Codex review the PR. Once approved, the job deploys and runs in parallel with the live Teradata job.
6
Sign-off
After 3 consecutive days of validated parallel-run data, Lufthansa does UAT and signs off. You stay the stream owner after sign-off too.
PROGRAM OVERVIEW
7

## Slide 8
SESSION 1 · DISCUSSION
Discussion points & open questions
Q
“Is PPL its own squad? I don't see it listed.”
No — PPL is folded into the Loyalty squad (Prashant's team owns it), which is why it doesn't appear as a separate row on the squad list.
Q
“Does matching mean count only, or exact values?”
Both. The bar is 100% value-level match (counts and aggregations), not just row counts — and not necessarily syntactically identical SQL, since Teradata and Databricks have different functionality. If a real 99.9% ceiling exists, that requires a documented exception and sign-off from the Lufthansa squad owners, not a unilateral call by the delivery team.
Q
“‘Families’ is in this session's title — what is it?”
This term was named in the meeting title but wasn't defined in the recorded portion of this session (time ran short). Flag it with your pod lead or in a follow-up session rather than assuming a definition.
Q
“Who do I ask if I'm not yet mapped to a squad?”
Raise it immediately in session — Fathima / your pod lead action same-day squad mapping for anyone whose onboarding or Lufthansa ID is still pending.
SESSION 1 · DISCUSSION
8

## Slide 9
SESSION 1 · REFERENCE
Glossary: key terms from this session
Stream — One end-to-end Databricks job/pipeline; the atomic unit of migration.
Community — A group of streams released together as one milestone (0–10).
Squad — A business-domain grouping (ADW, B2B, Loyalty, etc.).
Wave — The deployment order within a community, based on dependency.
Freeze period — A window in which a community's streams can't be changed by the client without sign-off.
Lift-and-shift — Migrating Teradata logic as-is to Databricks, not modernizing or redesigning it.
LHID — Lufthansa ID — required for repo, Databricks, and system access.
Sign-off — Lufthansa's formal approval after UAT, following 3 days of validated parallel-run data.
SESSION 1 · REFERENCE
9

## Slide 10
BRINGING IT TOGETHER
Your Session-1 checklist
1
Confirm your squad mapping and LHID access status today — don't wait if either is missing.
2
Locate the master tracking Excel and the lineage document for your squad.
3
Identify which community and wave you're currently working in, and its freeze status.
4
Walk through the full stream lifecycle (dev → PR → pre-prod → sign-off) before you start.
5
Bring the “Families” question — and anything else unresolved — to your pod lead.
Questions or gaps in this deck? Loop in your pod lead — several answers (squad mapping, sign-off exceptions) are meant to be resolved 1:1.
SESSION 1 · PROGRAM OVERVIEW
10